TERMS OF REFERENCE

RAINWATER AND FLASH FLOOD HARVESTING STUDY IN FOUKA AREA, MATROUH GOVERNORATE, EGYPT.

Date [July 2026]

TABLE OF CONTENTS

1	BACKGROUND of the assignment	3

1.1	INTRODUCTION TO THE PROJECT	3

1.2	GENERAL BACKGROUND OF THE ACTIVITY	3

2	OBJECTIVES & EXPECTED RESULTS of the Activity	4

2.1	AIM AND OBJECTIVE(S)	4

2.1.1	Specific Objectives	4

2.2	TARGET GROUP AND AREA	5

2.2.1	TARGET BENEFICIARIES	5

2.2.2	STAKEHOLDERS INVOLVED	5

2.2.3	TARGET AREA (NATIONAL, SUBNATIONAL, LOCAL)	5

3	SCOPE OF WORK, DELIVERABLES	6

3.1	TASKS AND EXPECTED RESULTS	6

3.2	DELIVERABLES	10

4	LOGISTICS AND TIME	10

4.1	COMMENCEMENT DATE AND Duration	10

4.2	SCHEDULE	11

4.3	Payment Schedule and Conditions	11

5	REQUIREMENTS	12

5.1	Consultant Qualifications and Experience	12

5.1.1	General Requirements	12

5.1.2	Technical Team Requirements	12

5.1.3	Required Supporting Documents	13

5.1.4	Evaluation Criteria	13

6	REPORTING REQUIREMENTS	13

6.1	OUTLINES OF THE EXPECTED REPORTS	13

# BACKGROUND of the assignment

## INTRODUCTION TO THE PROJECT

The proposed activity is part of a national effort led by the Ministry of Water Resources and Irrigation. The project is developed following the preparation of a concept note by the Strategic Sector of the Ministry and aims to address critical water management challenges in Egypt’s northwestern coastal region, this initiative is aligned with national priorities for enhancing water security and climate resilience, particularly in arid and semi-arid regions. It also supports broader objectives of sustainable water resources management, adaptation to climate change, and the promotion of nonconventional water resources.

The project focuses on the design and implementation of a pilot system for rainwater and flash flood harvesting in the FOUKA area, located in Marsa Matruh. It is expected to contribute to improving water availability, supporting agricultural development, and enhancing the resilience of local communities to climate variability, Furthermore, the activity aligns with international and regional priorities supported by the European Union in the field of water management, climate adaptation, and sustainable development in the Southern Mediterranean region.

## GENERAL BACKGROUND OF THE ACTIVITY

The FOUKA area, situated along Egypt’s northwestern coastal zone in Matrouh Governorate, is characterized by a semi-arid climate with limited and highly variable rainfall, estimated at approximately 90–120 mm per year. Precipitation occurs mainly in short, intense storm events, which frequently generate flash floods.

Due to the geomorphological and soil characteristics of the area, these events result in rapid surface runoff, limited groundwater recharge, and significant soil erosion. Consequently, a large portion of the available water is lost without effective utilization, exacerbating water scarcity conditions in the region.

These challenges are further intensified by climate change, which is expected to increase the frequency and intensity of extreme weather events across North Africa. This situation poses significant risks to water security, agricultural productivity, and the livelihoods of local communities, particularly Bedouin populations who depend on rain-fed systems.

However, the region also presents significant opportunities. Recent studies and field assessments have demonstrated that integrated rainwater harvesting and flash flood management systems—when properly designed based on local hydrological, geological, and socio-economic conditions—can effectively capture and store runoff water. Techniques such as check dams, earth barriers, small ponds, and underground tanks have shown strong potential to enhance water availability, support sustainable agriculture, and improve ecosystem resilience.

In this context, the ministry of water resources and irrigation of Egypt has identified the need to develop a pilot intervention in the FOUKA area to demonstrate the feasibility and effectiveness of such systems. The proposed activity will build on existing scientific knowledge, including GIS-based analysis and hydrological modeling, to design and implement a sustainable rainwater and flash flood harvesting system tailored to local conditions.

The activity is expected to contribute to national efforts toward improving water resource efficiency, strengthening climate resilience, and promoting sustainable rural development in water-scarce regions.

# OBJECTIVES & EXPECTED RESULTS of the Activity

## AIM AND OBJECTIVE(S)

The overall aim of this activity is to enhance water security and climate resilience in the FOUKA area of Matrouh Governorate through the development and implementation of sustainable rainwater and flash flood harvesting systems adapted to local environmental and socio-economic conditions.

### Specific Objectives

In order to achieve the above aim, the activity will pursue the following specific objectives:

- To identify and assess suitable locations for rainwater and flash flood harvesting structures using integrated hydrological, geological, and GIS-based analysis.

- To design and implement a pilot rainwater harvesting system (such as check dams, cisterns, or underground tanks) tailored to the specific conditions of the FOUKA area.

- To evaluate the technical, hydrological, geological, and socio-economic feasibility and performance of the proposed system.

- To strengthen the technical and institutional capacities of local stakeholders and communities for the sustainable management, operation, and maintenance of water harvesting systems.

In order to achieve the above objectives, the Ministry of Water Resources and Irrigation, represented by Groundwater Sector, will engage the services of a qualified consulting entity (hereinafter referred to as the “Consultant”) to support the implementation of this activity.

The Consultant will be selected based on demonstrated experience and proven expertise in the field of rainwater harvesting and flash flood management, as well as the qualifications and competencies of its technical staff. The evaluation process will include both technical and financial assessments, with emphasis placed on the technical quality of the proposal, methodology, relevant experience in similar projects, and the qualifications of the proposed team. Financial proposals will be evaluated in relation to the scope of services, level of effort, and cost-effectiveness of the proposed approach. Preference will be given to technically qualified consultants offering the most economically advantageous proposal and the lowest financial cost, provided that all technical requirements and quality standards are fully satisfied. Entities with a strong track record in similar projects, particularly in arid and semi-arid environments, will be prioritized.

All tasks and subtasks assigned to the Consultant will be carried out under the supervision and in close coordination with the Ministry’s designated technical team, to ensure alignment with national priorities, technical standards, and project objectives.

## TARGET GROUP AND AREA

### TARGET BENEFICIARIES

The main partners and beneficiaries of the project are:

| Partner (Main Beneficiary) | Name of Institution: Ministry of Water Resources and Irrigation (MWRI) Contact person’s First Name: Reham Contact person’s Last Name: Elkorashey Title and position: Professor, Project Manager Email: reswater.mwri@gmail.com reham.elkorashey@gmail.com Mobile: 01002869934 |
| --- | --- |
| Other beneficiaries | Names of institutions: Groundwater Sector (GWS)-MWRI. |
| Local Community / Final Beneficiaries | Bedouin communities, small-scale farmers, and pastoralists in the Fouka pilot catchment area. |

### STAKEHOLDERS INVOLVED

The stakeholders that will be involved in the project are:

1. Municipalities

2. Water Authorities

3. Technicians working in the water sector

4. General Public

### TARGET AREA (NATIONAL, SUBNATIONAL, LOCAL)

The activity will be implemented at the local level in the FOUKA area, located along the northwestern coastal zone of Egypt within Matrouh Governorate. The area lies approximately 70 km east of Marsa Matruh and in close proximity to Ras El Hekma.

The study area extends inland from the Mediterranean coastline and is characterized by a network of wadis draining toward the sea. It is situated near the Dabaa–Matruh coastal road and is well connected through the regional road network, facilitating accessibility for field investigations and implementation activities.

The selected area has been identified based on its high potential for rainwater and flash flood harvesting, as well as its vulnerability to water scarcity and exposure to periodic flash flood events. These characteristics make it a priority location for interventions aimed at improving water resource management and enhancing climate resilience.

The primary beneficiaries in the area include local Bedouin communities, whose livelihoods depend on rain-fed agriculture and pastoral activities. The proposed activity aims to support these communities by improving access to water resources for domestic use, livestock, and small-scale agriculture, while also contributing to the mitigation of flash flood risks.

As illustrated in Figure (1), the study area is delineated along the coastal strip near FOUKA, highlighting key features such as the main road network, existing settlements, and drainage patterns.

Fig. (1) General Location of the study area.

# SCOPE OF WORK, DELIVERABLES

## TASKS AND EXPECTED RESULTS

The Consultant shall adopt a multidisciplinary approach combining field investigations, GIS and remote sensing analysis, hydrological and hydraulic modeling, and socio-economic assessment to achieve the objectives of the project in the FOUKA area, located in Matrouh Governorate.

The project shall include, but not be limited to, the following tasks:

Task 1: Data Collection, and GIS-Based Analysis

Description:

Collect, review, and analyze all relevant available data required for the study.

Activities include:

- Compilation of meteorological, hydrological, geological, and topographical data.

- Acquisition and processing of satellite imagery and Digital Elevation Models (DEMs).

- GIS-based delineation of catchments and drainage networks.

- Identification of potential runoff zones and preliminary suitable locations for water harvesting.

Expected Result:

A comprehensive geospatial database and maps identifying priority areas for rainwater harvesting.

Task 2: Field Investigations and Site Assessment

Description:
Conduct field surveys to validate and complement desk-based analysis.

Activities include:

- Ground-truthing of GIS outputs.

- Soil characterization and infiltration testing.

- Geophysical investigations to assess subsurface conditions.

- Surveying of selected sites (topographic and hydrological features).

Expected Result:

Validated field data and detailed site characterization for design purposes.

Task 3: Hydrological and Hydraulic Modeling

Description:
Develop and apply appropriate hydrological and hydraulic models to simulate runoff and support system design.

Activities include:

- Application of models such as HEC-HMS and/or SWAT for rainfall–runoff simulation

- Estimation of runoff volumes for different return periods

- Flood routing and peak discharge estimation

- Hydraulic analysis to support sizing and performance of proposed structures

Expected Result:

Quantified runoff potential and design parameters for water harvesting structures.

Task 4: Socioeconomic Assessment Description:

Description:
Assess local community needs and potential socio-economic benefits of the project.

Activities include:

- Pilot Area Characterization and Future Water Assessment

The Consultant shall prepare a characterization report for the pilot catchment area in FOUKA, based on the developed assessment framework, evaluating current and future water demand and water availability within the study area up to the year 2050.

Different types of catchment conditions within the study area shall be assessed to support a comprehensive evaluation and testing of the proposed framework under varying environmental and hydrological conditions.

The characterization report shall focus on the different water uses within the area, including domestic, agricultural, and livestock demands, in order to assess the potential for decentralized rainwater harvesting and non-conventional water resource applications.

- Identification of water use patterns (domestic, livestock, agriculture).

- Stakeholder consultations and community engagement.

- Assessment of potential livelihood improvements.

- Evaluation of social acceptance and sustainability.

Expected Result:

A socio-economic assessment report supporting the design and implementation strategy.

Task 5: Design of Water Harvesting Structures and Tender Documents

Description:

Prepare and evaluate integrated technical alternatives for the proposed pilot rainwater harvesting system and develop complete engineering designs and tender documents for the selected option.

Activities include:

- Identification and proposal of different suitable rainwater harvesting alternatives and structures (e.g., check dams, cisterns, storage tanks, recharge structures, sedimentation basins, and conveyance channels)

- Development of integrated system layouts linking runoff collection, water conveyance, storage, distribution, and utilization

- Comparative assessment of the proposed alternatives based on:

- technical performance

- hydraulic efficiency

- economic feasibility and cost

- operation and maintenance requirements

- durability and sustainability

- environmental and social considerations

- Multi-criteria evaluation to support owner decision-making and selection of the preferred alternative

- Hydraulic and structural design calculations for the selected alternative

- Design of sediment control and water quality improvement measures to minimize sediment accumulation and improve harvested water quality

- Preparation of detailed engineering drawings, technical specifications, and Bills of Quantities (BOQs)

- Development of cost estimates and tender documents for implementation

Expected Result:

Complete design package and tender-ready documentation for implementation.

Task 6: Development of Upscaling Strategy and Site Selection Criteria

Description:

Develop a methodology for replicating and scaling up the pilot project in other suitable areas.

Activities include:

- Identification of key criteria for site selection, including:

- Rainfall characteristics and runoff potential.

- Catchment size and topography.

- Soil type and infiltration capacity.

- Proximity to communities and land use.

- Socio-economic needs and feasibility.

- Development of a GIS-based suitability model for identifying priority areas.

- Preparation of a roadmap for scaling up the intervention at regional level.

Expected Result:
A clear and applicable framework for replication and expansion of rainwater harvesting systems.

Task 7: Monitoring and Evaluation System for Pilot Structures

Description:

Develop and implement a monitoring system to assess the performance of the constructed structures.

Activities include:

- Design of a monitoring plan for rainfall events and system response

- Installation (or proposal) of simple monitoring tools (e.g., Rainfall gauges, water level indicators)

- Monitoring of:

- Rainfall intensity and duration

- Runoff generation

- Storage levels in tanks/cisterns

- Inflow and outflow (discharge) rates

- Development of data recording and reporting protocols

- Evaluation of system performance during and after rainfall events

Expected Result:

A functional monitoring framework enabling performance evaluation and future optimization.

## DELIVERABLES

The table below lists all the expected deliverables.

| Tasks | Deliverables |
| --- | --- |
| Task 1: Data Collection & GIS Analysis | D1. Inception Report including detailed methodology, work plan, and compiled geospatial database (GIS maps, DEM analysis, catchment delineation). |
| Task 2: Field Investigations | D2: Field Survey Report including Survey Data, soil analysis, infiltration tests, geophysical investigations, and validated site conditions. |
| Task 3: Hydrological & Hydraulic Modeling | D3: Hydrological and Hydraulic Modeling Report including runoff simulations, flood analysis, and design parameters for different return periods. |
| Task 4: Socioeconomic Assessment | D4: Socioeconomic Assessment Report including stakeholder analysis, water demand, and livelihood impact assessment. |
| Task 5: Design & Tender Documents | D5: Detailed Design Report including hydraulic/structural designs, engineering drawings, BOQs, cost estimates, and tender documents. |
| Task 6: Upscaling Strategy | D6: Upscaling and Replication Strategy Report including site selection criteria, GIS suitability model, and expansion roadmap. |
| Task 7: Monitoring System | D7: Monitoring and Evaluation Plan including methodology, indicators, data collection tools, and performance assessment framework. |

# LOGISTICS AND TIME

## COMMENCEMENT DATE AND Duration

The implementation of the activity will be carried out over an estimated period of 4 months from the date of contract signature.

This duration covers all phases of the project, including study, analysis, design, tendering support, monitoring, and reporting.

## SCHEDULE

A time table for the duration of the intended activities is shown below.

| Task | M i | M ii | M iii | M 1 | M 2 | M 3 | M 4 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOR preparation |  |  |  |  |  |  |  |
| TOR approval |  |  |  |  |  |  |  |
| Contracting |  |  |  |  |  |  |  |
| Task 1: Data Collection & GIS Analysis |  |  |  |  |  |  |  |
| Task 2: Field Investigations |  |  |  |  |  |  |  |
| Task 3: Hydrological & Hydraulic Modeling |  |  |  |  |  |  |  |
| Task 4: Socioeconomic Assessment |  |  |  |  |  |  |  |
| Task 5: Design & Tender Documents |  |  |  |  |  |  |  |
| Task 6: Upscaling Strategy |  |  |  |  |  |  |  |
| Task 7: Monitoring System |  |  |  |  |  |  |  |

## Payment Schedule and Conditions

Payments to the Consultant shall be made according to the approved deliverables and the following payment schedule:

| Payment Stage | Description | Percentage |
| --- | --- | --- |
| Advance Payment | Upon contract signature and commencement of the assignment | 20 % |
| Payment 2 | Upon submission and approval of Deliverables D1 to D4 | 30 % |
| Final Payment | Upon submission and approval of Deliverable D5 to D7, including the Final Report, subject to approval. | 50 % |

All payments shall be subject to the review, revision, and formal approval of the submitted deliverables by the Ministry of Water Resources and Irrigation or its designated technical committee.

The Consultant shall revise and resubmit deliverables, if required, to address comments received from the Ministry prior to payment approval.

# REQUIREMENTS

## Consultant Qualifications and Experience

The Consultant shall be a qualified consulting firm or consortium with demonstrated experience in the design and implementation of rainwater harvesting and flash flood management systems, particularly in arid and semi-arid environments.

### General Requirements

The Consultant must demonstrate:

- Proven experience in rainwater harvesting systems in wadi systems and dryland areas similar to those in Matrouh Governorate.

- Experience in hydrological and hydraulic modeling (e.g., HEC-HMS, SWAT, or similar tools.

- Experience in GIS and remote sensing applications for water resources assessment

- Proven track record in design and supervision of hydraulic structures (e.g., check dams, cisterns…).

- Experience in socio-economic studies related to water use and rural livelihoods.

- Experience in capacity building and stakeholder engagement.

- Previous experience in similar projects funded by national or international organizations is an asset.

### Technical Team Requirements

The Consultant shall provide a multidisciplinary team including, but not limited to, the following key experts:

- Team Leader / Water Resources Expert

- Advanced degree in water resources engineering or related field

- Minimum 10 years of experience

- Proven experience in similar projects

- Hydrologist / Hydraulic Modeler

- Experience in hydrological modeling and flood analysis

- Experience with rainfall-runoff modeling tools

- GIS and Remote Sensing Specialist

- Experience in spatial analysis, DEM processing, and mapping

- Structural Design Engineer

- Experience in structural Engineering.

- Socioeconomic Expert

- Experience in community assessments and livelihood studies

### Required Supporting Documents

The Consultant shall submit the following documents:

- Company profile, including relevant project experience.

- List of similar projects completed in rainwater harvesting and related fields.

- Curriculum Vitae (CVs) of all proposed experts

- Copies of academic and professional certificates.

- Description of the technical approach and methodology.

- Organizational structure and team composition.

- Any supporting documents demonstrating technical and financial capacity.

### Evaluation Criteria

Selection of the Consultant will be based on the following criteria:

- the average annual turnover of the tenderer must exceed the annualized maximum budget of the contract (2.7 million EGP) i.e. the maximum budget stated in the contract notice divided by the initial contract duration in years, where this exceeds 1 year.

- the tenderer has provided the same or similar services as those required in this tender during any of the last 10 years with a cumulated budget of at least that of this contract.

- Upon completion of the technical evaluation, the envelopes containing the financial offers for tenders that were not eliminated during the technical evaluation will be opened (i.e. those with an average score of 75 points or more (out of 100)). Tenders exceeding the maximum budget available for the contract will not be accepted and will therefore not be further evaluated.

- The technical score shall be based on the following criteria:

  - Proposal Approach and Methodology: 10%

  - Service Programme & Team composition:10%

  - Qualification and Engagement of Key Experts: 50%

  - Experience of the Consultant/Organization with international funding agencies, UN regional organization as ESCWA, or League of Arab States (LAS) as ACSAD: 15%

  - Experience in design and construction of Nashu wells, Harvesting cisterns, check dams, percolation tanks, recharge wells, and contour bunding: 15%

- The best price-quality ratio is established by weighing technical quality against price on an 80/20 basis.

# REPORTING REQUIREMENTS

## OUTLINES OF THE EXPECTED REPORTS

The deliverables shall be submitted in English in electronic form. The deliverables will have the following main sections (content to be further defined):

Acknowledgements

Executive Summary

- 1. Background

- 2. Introduction

- 3. Methodology

- 4. Chapter 1

- 5. Chapter 2

- 6. Chapter 3

- 7. Chapter 4

- 8. Recommandations

- 9. Annexes